## Workstream Log
Vivifi - Burn Down Workstream Chart
| Task Name | Description/Notes | Assigned To | Time Estimate (days) | Priority | Status
| Create index page |  | Nick | 0.5 | 10 | Complete
| Create database |  |  | 2 | 10 | Complete
| Add contact page |  |  | 0.25 | 10 | Complete
| Administrator log-in page |  | Jason | 1 | 20 | Complete
| Create ensemble search page | Search engine for ensembles |  | 2 | 20 | Complete
| Ensemble personal page |  |  | 2 | 20 | Complete
| Solo musician search page |  |  | 1 | 30 | Complete
| Build-a-ensemble page |  |  | 1 | 30 | Not started
| Create event page |  |  | 2 | 40 | Complete
| Create registration pages |  |  | 2 | 40 | Complete
| Create 4 button menu | Artists/Ensemble/Ask Us/Vivibook | Nick | 3 | 40 | Complete
| Add about us page | Company info + links to artist registration page |  | 0.5 | 50 | Complete
| Add coming soon page |  |  | 0.5 | 50 | Complete
| Create contact form | Contact clients, apply for Vivifi service as artist, register as artist or planner |  | 1 | 50 | Complete
| Adopt site to Drupal |  |  | 1 | 60 | In progress
| Create Planners Form/Email |  | Jason | 1 | 60 | Complete
| Create FAQ page |  | Nick | 1 | 60 | Complete
| Update burndown chart |  | Jessa | 0.5 | 70 | Complete
| Style forms | (artist/ensemble/planner/contact/search) | Alex | 1.5 | 70 | Complete
| Add Instructions to all forms |  | Jason | 0.5 | 70 | Complete
| Style static pages | (home, aboutus, faq, artists, ens) | Chirstian | 0.5 | 70 | Complete
| Drupal Conversion | Update vivifievents.com to drupal | Jason | 4 | 70 | In progress
| Ajax Module | Link/Edit Forms to work with a Database | - |  | 70 | Not started
| Validation Test #1 | test art/ens/pln forms only allow logged in users to submit | Alex | 0.25 | 70 | In progress
| Validation Test #2 | test art/ens/pln forms forms can only be submitted once | Jessa | 0.25 | 70 | In progress
| Functionality Tests #1 | test art/ensemble/pln forms properly email admin@vivifievents.com | Christian | 0.25 | 70 | In progress
| Update Product Backlog | V.04 | Jason | 0.5 | 70 | In progress
Task Name…
Task Name…
Task Name…

## Burn Down Chart
Vivifi - Release Burn Down Chart
Iteration 1 |  | Release: | Points: | Points Remaining: | Notes: | Holidays |  | Applicable?
Start Date: | 2014-09-12 | 0.1 | 100 | 600 |  | New Year's Day | 2014-01-01 | No
End Date: | 2014-12-02 | 0.2 | 200 | 500 |  | Martin Luther King Jr.'s Day | 2014-01-20 | No
# of Developers: | 6 | 0.3 | 300 | 450 | Database dev delayed | Memorial Day | 2014-05-26 | No
Efficiency Factor | 0.7 | 0.4 | 400 | 350 | Convert site to new Requirements | Independence Day | 2014-07-04 | No
Work Days Total | 58 | 0.5 | 500 | 200 | Caught up with new requirements | Labor Day | 2014-09-01 | No
Dev Days Total | 348 | 0.6 | 600 |  |  | Veteran's Day | 2014-11-11 | Yes
# of Task Work Days | 243.6 | 1 | 700 |  |  | Thanksgiving Day | 2014-11-28 | Yes
[6 empty] | Christmas Day | 2014-12-25 | No